**Georgian College institutional**

**Research health sciences programs (1)**

**Project status report**

Reporting Period: September 26th to October 3rd

Project Start Date: 5th July 2018 Project End Date: 5th December 2018

Current Status: Preparing Analysis Plan.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Task** | **Assigned to** | **Begin Date** | **Completion Date** | **Status** |
| Collect the data from the client | Akshay Veeramaneni, Yashwanth Pailla | September 14 | September 17 | **Received** |
| Team Meeting | Project Team |  | September 19 | **As Planned** |
| Perceiving the data | Project Team | September 17 | September 20 | **Completed** |
| Cleaning the data provided by the client | Ajith Stephen, Akshay Veeramaneni | September 20 | September 25 | **Completed** |
| Missing value analysis | Harshaditya G Devabhaktuni | September 20 | September 25 | **Completed** |
| Exploratory analysis | Akshay Veeramaneni, Roshan Cintury | September 20 | September 25 | **Completed** |
| Outlier analysis | Ajith Stephen | September 20 | September 25 | **Completed** |
| Isolation of unnecessary information | Yashwanth Redddy Pailla | September 20 | September 25 | **Completed** |
| Team Meeting | Project Team |  | September 26 | **As Planned** |
| Identify programs to be analyzed | Harshaditya G Devabhaktuni | September 25 | September 28 | **Completed** |
| Team Meeting | Project Team |  | October 3 | **As Planned** |
| Prepare an Analysis Plan | Harshaditya G Devabhaktuni, Yashwanth Reddy Pailla | September 28 | October 5 | **At Risk** |
| Team Meeting | Project Team |  | October 10 | **As Planned** |
| Analyze the data to determine Graduation Rates for each of the selected programs in each of the years | Harshaditya G Devabhaktuni | October 6 | October 13 | **On Track** |
| Team Meeting | Project Team |  | October 17 | **As Planned** |
| Determine the Graduation Rate Trends for each of the selected programs | Roshan Cintury | October 14 | October 21 | **On Track** |
| Analyze the data for the Graduation Rates of similar programs offered by other Ontario colleges | Akshay Veeramaneni | October 22 | October 27 | **On Track** |
| Rank each of Georgian College’s Graduation Rate compared to those of other Ontario colleges | Yashwanth Reddy Pailla, Roshan Cintury | October 28 | November 2 | **On Track** |
| Team Meeting | Project Team |  | October 31 | **As Planned** |
| Qualify if each program is under-performing based on rank compared to other Ontario colleges | Ajith Stephen, Akshay Veeramaneni | November 3 | November 7 | **On Track** |
| Team Meeting | Project Team |  | November 7 | **As Planned** |
| Analyze Demographic Data to identify statistics which negatively affect Graduation Rates | Roshan Cintury, Harshaditya G Devabhaktuni | November 8 | November 13 | **On Track** |
| Team Meeting | Project Team |  | November 14 | **As Planned** |
| Conclude the results behind low graduation rates | Akshay Veeramaneni,Yashwanth Reddy Pailla | November 14 | November 18 | **On Track** |
| Team Meeting | Project Team |  | November 21 | **As Planned** |
| Compare Georgian College’s criteria for entering their programs to those of other Ontario colleges offering similar programs which have higher Graduation Rates | Ajith Stephen, Harshaditya G Devabhaktuni, Roshan Cintury | November 18 | November 23 | **On Track** |
| Team Meeting | Project Team |  | November 28 | **As Planned** |
| Review all analysis for accuracy | Roshan Cintury | November 24 | November 30 | **On Track** |
| Summarize findings | Roshan Cintury | November 23 | November 26 | **On Track** |
| Conclusions | Ajith Stephen | November 26 | November 31 | **On Track** |
| High-level recommendations for enhancements to under-performing programs | Harshaditya G Devabhaktuni | December 1 | December 5 | **On Track** |
| Written Report | Project Team | September 14 | November 28 | **On Track** |
| PowerPoint Presentation | Roshan Cintury | September 14 | December 4 | **On Track** |
| Client presentation | Project Team |  | December 5 | **On Track** |
| Compile files and reports for delivery to the client | Team Report |  | December 5 | **On Track** |

Submitted by:

Ajith Stephen

Akshay Veeramaneni

Harshaditya G Devabhaktuni

Roshan Cintury

Yashwanth Reddy Pailla